## Job Cost
CoreBuilt Contracting LLC — Job Cost Summary March 2026
Job Number | Project Name | Client | Cost Type | Description | Units | Amount | Billing Status
JB-2041 | Maple Ridge Townhomes | Hartwell Development | Labor | Framing crew — week of Mar 3 | 320 hrs | 9600 | Billed — AIA Draw #7
JB-2041 | Maple Ridge Townhomes | Hartwell Development | Labor | Finish carpentry — weeks of Mar 10–17 | 280 hrs | 8400 | Billed — AIA Draw #7
JB-2041 | Maple Ridge Townhomes | Hartwell Development | Materials | Lumber & structural steel — Phase 3 | 1 lot | 18400 | Billed — AIA Draw #7
JB-2041 | Maple Ridge Townhomes | Hartwell Development | Materials | Drywall, insulation, roofing shingles | 1 lot | 11200 | Billed — AIA Draw #7
JB-2041 | Maple Ridge Townhomes | Hartwell Development | Subcontractors | Electrical rough-in — Rodriguez Electrical LLC | 1 job | 12500 | Billed — AIA Draw #7
JB-2089 | Civic Center Renovation | City of Millbrook | Labor | Project management — J. Park | 80 hrs | 4200 | Billed — AIA Draw #3
JB-2089 | Civic Center Renovation | City of Millbrook | Labor | Commercial finish crew — Mar full month | 480 hrs | 14400 | Billed — AIA Draw #3
JB-2089 | Civic Center Renovation | City of Millbrook | Materials | Commercial glazing + aluminum storefront | 1 lot | 12600 | Billed — AIA Draw #3
JB-2089 | Civic Center Renovation | City of Millbrook | Subcontractors | Plumbing rough-in — Premier Plumbing & HVAC | 1 job | 18200 | Billed — AIA Draw #3
JB-2074 | Ridgewood Estates Phase 2 | Private Client | Labor | Concrete & foundation crew — Mar 1–15 | 240 hrs | 7200 | Billed — Draw #4
JB-2074 | Ridgewood Estates Phase 2 | Private Client | Materials | Concrete, rebar, form materials | 1 lot | 19900 | Billed — Draw #4
JB-2074 | Ridgewood Estates Phase 2 | Private Client | Subcontractors | Foundation excavation — Atlas Foundation Services | 1 job | 24500 | Not Yet Billed
JB-2102 | Millbrook Office Park | Greenway Properties | Labor | Site prep + steel erection crew | 320 hrs | 9600 | Billed — AIA Draw #1
JB-2102 | Millbrook Office Park | Greenway Properties | Materials | Structural steel package — Phase 1 | 1 lot | 14000 | Billed — AIA Draw #1
JB-2102 | Millbrook Office Park | Greenway Properties | Subcontractors | HVAC ductwork rough-in — Summit HVAC | 1 job | 14200 | Billed — AIA Draw #1